## Instructions
Staff Planning Sheet: Instructions
EMERGENCY STAFF PLANNING SHEET
Time period (e.g. first week or first month)
|  | Function | Responsibility | CP Main Office | Field Offices | Region | ERT and Emergency Roster | TDY from Outside Region | HQ | Consultant
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
The "Function" is the category of work that the Responsibility falls under, for example, Communications and Media, or Staffing. We use this column to organize the Responsibilties into logical groupings (and thereby begin to define Scopes of Work or Job Descriptions)
START HERE
A "Responsibility" is the specific activity that must be undertaken. This column is esssentially the list of ALL the things to be done for the emergency during the time period stated at the top of the sheet.
These columns titles give you a prompt for the places where you might find people to cover each of the Responsibilities you list. In this section you can list names of people in each of these places who might be called upon to handle this responsibility.

## Example
Staff Planning Sheet: Example
EMERGENCY STAFF PLANNING SHEET
First 48 Hrs
|  | Function | Responsibility | Islamabad (lead) | Field Office | Region | ERT & Global Roster | TDY | HQ | Consultant
| 1 | Staffing | Recruit add’l staff as needed, technical staff and multi-taskers | J |  | K |  |  | G
| 2 | Staffing | Staff care & support | J/G
| 3 | Staffing | Designate senior staff as emergency coordination in partner location | J/A/GW
| 4 | Staffing | Check staff (staff locator) | J | HOO
| 5 | Staffing | Send regional team | G |  | K
| 6 | Staffing | Identify TDY staff from region for admin & finance |  |  | K
| 7 | Staffing | Plane & visa & $$ to get ready to go (regional team) | G |  | R
| 8 | Staffing | Contact ERT immediately | J |  | K
| 9 | Staffing | Contact other RDs for their staff |  |  | K
| 10 | Fin-Admin | Fin-Admin
| 11 | Fin-Admin | Ensure cash on hand | A
| 12 | Fin-Admin | Forms / procedures available (CD) | A
| 13 | Fin-Admin | Internal TDY/finance deployment | A | HOO
| 14 | Procurement | Procurement
| 15 | Procurement | Contact HQ procurement | M
| 16 | Procurement | Begin to organize procurement & supply systems | M/GW | Z
| 17 | Procurement | Request for quotations / identify potential vendors | M/Kh | Z
| 18 | HQ relations | HQ relations
| 19 | HQ relations | Contact RD à HQ and ERT | J
| 20 | HQ relations | Request $$ from HQ | J
| 21 | HQ relations | Contact web/fundraising unit at HQ to provide updated information, “help now” | Ch
| 22 | Media & Comm | Media & Comm
| 23 | Media & Comm | Contact Caroline | J
| 24 | Media & Comm | First sitrep prepared | A
| 25 | Media & Comm | Press release | DMT |  | C
| 26 | Media & Comm | Get photographs | (Jim)
| 27 | Media & Comm | Assign point person for media | J
| 28 | Media & Comm | Write talking points | DMT |  | C
| 29 | Media & Comm | Establish spokesperson (# information) | GW |  | C
| 30 | Media & Comm | Get communication person on ground | (Jim) |  | C
| 31 | Media & Comm | Make available means for CRS visibility / signage | DMT | HOO
| 32 | Fundraising | Fundraising
| 33 | Fundraising | Contact OFDA | DMT |  | K
| 34 | Coordination | Coordination
| 35 | Coordination | Dev'p coordination schedule | DMT
| 36 | Coordination | Coordinate with partners and organization | DMT |  | K
| 37 | Coordination | Coordination with UN and other NGOs | DMT
| 38 | Coordination | Telecon with CI / Rome | J |  | K
| 39 | Coordination | Contact primary CI partners bilaterally | J |  | K
| 40 | Partnership | Partnership
| 41 | Partnership | Meet with partners for immediate response & coordination | GW
| 42 | Partnership | Contact partner and bishop in location | J
| 43 | Partnership | Initial funding commitment to partner (authorize use of funds on hand) | J
| 44 | Assessments | Assessments
| 45 | Assessments | Gather general information of situation | GW
| 46 | Assessments | Assess Logistics, transportation, emergency supplies, communications (sta phone) | Farukh
| 47 | Assessments | Security & access assessment | Farukh
| 48 | Assessments | Map of disaster area | Aadil
| 49 | Assessments | Form joint assessment team (CRS & Partners) – request support from region as needed | DMT | HOO | K
| 50 | Assessments | Conduct rapid assessment with partners | PMs | PMs
| 51 | Assessments | Sent first team in field | DMT | HOO
| 52 | Assessments | Review assessment tools, organization rapid assessment | A (PMs)
| 53 | Immediate Relief | Immediate Relief
| 54 | Immediate Relief | Partners staff immediate relief
| 55 | Program Strategy | Program Strategy
| 56 | Program Strategy

## Template
EMERGENCY STAFF PLANNING SHEET
Time period (e.g. first week or first month)
| Function | Responsibility | CP Main Office | CP Field Office | Region | ERT & Global Roster | TDY from Outside Region | HQ | Consultant
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28