Sri Lanka Tsunami Case Study

Finance & Resource Management

Context:

CRS had no office in Sri Lanka when the tsunami hit.  CRS had a relationship with Caritas Sri Lanka (SEDEC) through funding a peace building program, managed from Delhi by a Regional Program Manager.

Day # 3 -7

- Bank Account at Colombo opened.

Weeks # 2

- TDYers as Finance Managers deployed in the field and at Colombo.

- Draft Finance policy and procedures manuals issued for field offices.

- CRS spending on behalf of the partner (SEDEC) for SOA activities initiated (this system continued for 3 months) in absence of financial and procurement structure at Partner offices at the Diocese and National level.

Weeks # 3 - 4

- ERT Finance Technical Advisor arrives at Colombo. He starts working on systems, procedures, policies and starts dealing with HQ on finance issues – specially implementation of Sun system in Sri Lanka.

- Sun Systems implemented.

- Kalmunai office yet to have a finance manager. The Base Manager handles finance duties.

- CRS – Sri Lanka send the first month end files to HQ.

- Procurement Policy, Field financial policies implemented.

- Process to open Bank accounts for each field office initiated.

- Decision to make the Partner offices computerized taken. Decision to implement Tally as the financial software at Partner offices undertaken.

- Recruitment of a finance Manager and a finance assistant done for the partner office at Galle.

Months # 2-3

- Training of finance undertaken for all financial managers, Diocesan Directors undertaken at the beginning of Month 2.

- Finance Manager deployed at Kalmunai.

- Training on Tally undertaken for finance staff.

- Implementation of Tally done at 5 Tsunami affected dioceses.

- SEDEC bank accounts opened and partners start spending directly (instead of CRS spending on their behalf).

- Mango (financial assessment tool) Assessment done at dioceses. (Not so well accepted).

- Partner finance staff in Kalmunai recruited.

What worked well:

- Using Sun Systems from start.

- Bring Finance Managers for CRS and recruit Partners finance staff immediately. CRS recruits, trains and manages the partners in the meantime.

- Have Partners use computerized accounting and inventory software.

- Open CRS accounts in the fields immediately to reduce cash transactions.

- Formal training and manual provided to partners in addition to on the job capacity building of partner finance staff.

Lessons learned: what would we do differently the next time

- Placement of staff at each office is most important.

- Staff deployed should be well informed on CRS policies and procedures, able to set up systems and train staff (not simply assess compliance).

- Have CRS systems, policies, tools in a ready to implement stage on day 1. This helps in more efficient deployment. A resource CD having all details should be developed.

- A standardized data entry system (for description) should be encouraged for the agency worldwide. Eg. Sri Lanka Sun Description policy or Europe Description policy.

- Use of standardized T1 codes for tracking different aspects of emergency like shelter, livelihoods etc.

- CRS needs a user friendly field financial system to tie up to Sun from day 1. (Finance software of CRS/India or Tally can be the options)

- Finance assessment should have a constructive focus rather than being like an audit.