## Sheet1
| FSP Tendering Quick Reference Guide Timeline |  |  |  | Week Commencing:
S# | Task Name | Days Time | Lead | Support | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | #VALUE! |  |  |  |  | #VALUE! |  |  |  |  | #VALUE! |  |  |  |  | #VALUE! |  |  |  |  | #VALUE! |  |  |  |  | #VALUE!
[5 empty] | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1 | Review Treasury Policies: | 2 hr | PM, Proc | HoOP, FM | bar: Week 1 Day 1
2 | Develop the FSP SoW | 2 day | PM | Cash TA | bar: Week 1 Day 1 to Week 1 Day 2
3 | Draft Procurement Activity Plan | 2 hr | Proc | All | bar: Week 1 Day 1
4 | Procurement Email Address | 2 days | Proc | IT | bar: Week 1 Day 1 to Week 1 Day 2
5 | Conduct FSP SoW Review Meeting | 1 hr | PM, Cash TA | HoOP, Proc | bar: Week 1 Day 3
6 | Contact CP Primary Banking Institution | 1 hr | FM | PM | bar: Week 1 Day 4
7 | Meet with the Global Treasury Manager | 1 hr | PM, Proc, HooP | GTM | bar: Week 1 Day 5
8 | Develop a Bid Committee | 2 hr | Proc | HoOP, PM | bar: Week 1 Day 5
9 | Draft Expression of Interest (EOI) | 2 hr | Proc | PM | bar: Week 1 Day 3
10 | Advertise EoI | 1-2 wk | Admin | Proc | bar: Week 2 Day 1 to Week 2 Day 5
11 | Review & Shortlist EoI | 1/2 day | Bid Com | Proc | bar: Week 3 Day 1
12 | Draft the Request for Proposal (RFP): | 5 day | Proc, PM | HoOP, Cash TA | bar: Week 2 Day 1 to Week 2 Day 5
13 | RFP - FSP Proposal Submission Timeline | 2-4 wk | Admin | Proc | bar: Week 3 Day 2 to Week 5 Day 1
14 | Draft Evaluation Criteria | 2 day | Proc | PM | bar: Week 3 Day 2 to Week 3 Day 3
15 | Evaluation Criteria Validation | 1 day | Bid Com | Proc | bar: Week 3 Day 4
16 | Pre-Bid Conference | 1/2 day | Proc, PM | HooP | bar: Week 3 Day 4
17 | Bid Opening | 2 hr | Proc | Bid Com | bar: Week 5 Day 2
18 | Bid Evaluation Process | 2 days | Proc | Bid Com | bar: Week 5 Day 3 to Week 5 Day 4
19 | Interview Process | 3 days | Proc | Bid Com | bar: Week 6 Day 1 to Week 6 Day 3
20 | Negotiation | 3 days | Proc | HoOp, PM | bar: Week 6 Day 4 to Week 7 Day 1
21 | Selection of Winning Bidder | 1 hr | Bid Com | Proc | bar: Week 7 Day 2
22 | Due Diligence | 1/2 day | Proc, PM | HoOP | bar: Week 7 Day 3
23 | Approval of the FSP of Choice | 1 day | HoP/CoP, CR, GTM | Proc, PM | bar: Week 7 Day 4
24 | Contracting Process | 2-4wk | HoOP | OGC | bar: Week 2 Day 1 to Week 7 Day 5
NOTE: This timeline is an example reflecting a 1 week EoI and 2 week FSP proposal submission timeline, but should be developed by the team to fit the needs of the context.
Note on B50: Weatherall, Jennifer: Confirm process - for mobile money it will be slightly different as per Mobile Money Policy
Note on B61: Weatherall, Jennifer: These all require a sub-section each and more detailed steps/activities but just putting in as a place holder to work back from the distirbution timing